## Tracker
ID | Track | Title | A/B ⚡ | Claude Model | OpenAI Model | Effort | Dependencies | Branch Base | Branch /claude | Branch /gpt | Status | Winner | Log File | Review File | Date Started | Date Done | Notes | Prompt File
C0 | C | Schema Migrations (Phase 0) | ⚡ Yes | sonnet-4-6 | gpt-5.3-codex | Small | None | feature/C0-schema-foundation | feature/C0-schema-foundation/claude | feature/C0-schema-foundation/gpt | ⬜ Not started | — | docs/codex/log/C0-schema-migrations.md | docs/codex/reviews/C0-adversarial-review.md | — | — |  | docs/codex/track-C/C0-schema-migrations.md
A0 | A | Critical Bug Fixes | ⚡ Yes | sonnet-4-6 | gpt-5.3-codex | Small | None | feature/A0-critical-fixes | feature/A0-critical-fixes/claude | feature/A0-critical-fixes/gpt | ⬜ Not started | — | docs/codex/log/A0-critical-fixes.md | docs/codex/reviews/A0-adversarial-review.md | — | — |  | docs/codex/track-A/A0-critical-fixes.md
B0 | B | Scaffold + Design System | ⚡ Yes | opus-4-6 | gpt-5.4 | Medium | None | feature/B0-react-scaffold | feature/B0-react-scaffold/claude | feature/B0-react-scaffold/gpt | ⬜ Not started | — | docs/codex/log/B0-react-scaffold.md | docs/codex/reviews/B0-adversarial-review.md | — | — |  | docs/codex/track-B/B0-scaffold-design-system.md
C1 | C | Missing API Endpoints | — | sonnet-4-6 | gpt-5.3-codex | Small | C0 | feature/C1-missing-endpoints | — | — | ⬜ Not started | — | docs/codex/log/C1-missing-api-endpoints.md | — | — | — |  | docs/codex/track-C/C1-missing-api-endpoints.md
C2 | C | Push Notifications (FCM) | — | sonnet-4-6 | gpt-5.3-codex | Medium | C0 | feature/C2-push-notifications | — | — | ⬜ Not started | — | docs/codex/log/C2-push-notifications.md | — | — | — |  | docs/codex/track-C/C2-push-notifications.md
A1 | A | Community Board | — | sonnet-4-6 | gpt-5.3-codex | Medium | C0, A0 | feature/A1-community-board | — | — | ⬜ Not started | — | docs/codex/log/A1-community-board.md | — | — | — |  | docs/codex/track-A/A1-community-board.md
B1 | B | Auth + RBAC + Permissions | — | sonnet-4-6 | gpt-5.4 | Medium | C0, B0 | feature/B1-auth-rbac | — | — | ⬜ Not started | — | docs/codex/log/B1-auth-rbac.md | — | — | — |  | docs/codex/track-B/B1-auth-rbac-permissions.md
A2 | A | User Search + Profile | — | sonnet-4-6 | gpt-5.3-codex | Medium | A1 | feature/A2-user-search-profile | — | — | ⬜ Not started | — | docs/codex/log/A2-user-search-profile.md | — | — | — |  | docs/codex/track-A/A2-user-search-profile.md
B2 | B | Event Ops Screen + SSE + FCM | — | sonnet-4-6 | gpt-5.4 | Medium | B1, C2 | feature/B2-event-ops | — | — | ⬜ Not started | — | docs/codex/log/B2-event-ops-screen.md | — | — | — |  | docs/codex/track-B/B2-event-ops-screen.md
C3 | C | Image Assets Architecture | ⚡ Yes | opus-4-6 | gpt-5.4 | Large | C0 | feature/C3-image-assets | feature/C3-image-assets/claude | feature/C3-image-assets/gpt | ⬜ Not started | — | docs/codex/log/C3-image-assets.md | docs/codex/reviews/C3-adversarial-review.md | — | — |  | docs/codex/track-C/C3-image-assets-architecture.md
C4 | C | Platform Config + API Key Status | — | sonnet-4-6 | gpt-5.4-mini | Small | C0 | feature/C4-platform-config | — | — | ⬜ Not started | — | docs/codex/log/C4-platform-config.md | — | — | — |  | docs/codex/track-C/C4-platform-config.md
A3 | A | Perks / Sponsors Display | — | sonnet-4-6 | gpt-5.3-codex | Small | A2 | feature/A3-perks-display | — | — | ⬜ Not started | — | docs/codex/log/A3-perks-sponsors.md | — | — | — |  | docs/codex/track-A/A3-perks-sponsors.md
B3 | B | Admin Parity (all screens) | — | sonnet-4-6 | gpt-5.3-codex | Large | B1, C1 | feature/B3-admin-parity | — | — | ⬜ Not started | — | docs/codex/log/B3-admin-parity.md | — | — | — |  | docs/codex/track-B/B3-admin-parity.md
D0 | D | Moderation Pipeline (Haiku→Sonnet) | ⚡ Yes | opus-4-6 | gpt-5.4 | Large | C0, A1 | feature/D0-moderation-pipeline | feature/D0-moderation-pipeline/claude | feature/D0-moderation-pipeline/gpt | ⬜ Not started | — | docs/codex/log/D0-moderation-pipeline.md | docs/codex/reviews/D0-adversarial-review.md | — | — |  | docs/codex/track-D/D0-moderation-pipeline.md
D1 | D | Analytics Pipeline (DuckDB) | — | sonnet-4-6 | gpt-5.3-codex | Medium | C0 | feature/D1-analytics-pipeline | — | — | ⬜ Not started | — | docs/codex/log/D1-analytics-pipeline.md | — | — | — |  | docs/codex/track-D/D1-analytics-pipeline.md
D2 | D | Event Wrap Reports | — | sonnet-4-6 | gpt-5.4 | Medium | D0, D1 | feature/D2-event-wrap-reports | — | — | ⬜ Not started | — | docs/codex/log/D2-event-wrap-reports.md | — | — | — |  | docs/codex/track-D/D2-event-wrap-reports.md
E0 | E | Jobs Schema + Backend API | — | sonnet-4-6 | gpt-5.3-codex | Medium | C0 | feature/E0-jobs-schema-api | — | — | ⬜ Not started | — | docs/codex/log/E0-jobs-schema-backend.md | — | — | — |  | docs/codex/track-E/E0-jobs-schema-backend.md
E1 | E | Jobs Board Social UI (Flutter) | — | sonnet-4-6 | gpt-5.3-codex | Large | E0, A1 | feature/E1-jobs-social-ui | — | — | ⬜ Not started | — | docs/codex/log/E1-jobs-board-flutter.md | — | — | — |  | docs/codex/track-E/E1-jobs-board-flutter.md
E2 | E | Hire Confirmation + Ratings | — | sonnet-4-6 | gpt-5.4 | Medium | E0, D0 | feature/E2-hire-confirmation | — | — | ⬜ Not started | — | docs/codex/log/E2-hire-confirmation.md | — | — | — |  | docs/codex/track-E/E2-hire-confirmation-ratings.md
E3 | E | Job Poster Account Portal | — | sonnet-4-6 | gpt-5.4 | Large | E0 | feature/E3-job-poster-portal | — | — | ⬜ Not started | — | docs/codex/log/E3-job-poster-portal.md | — | — | — |  | docs/codex/track-E/E3-job-poster-portal.md

## Legend
Status Values
⬜ Not started | Prompt not yet executed
🔵 In progress | Model currently executing this prompt
🟡 Claude done | Claude branch complete; awaiting GPT or review
🟡 GPT done | GPT branch complete; awaiting Claude or review
🟠 Under review | Both branches done; adversarial panel running
✅ Merged | Winner branch squash-merged to integration
🔴 Needs fixes | Review identified issues; rework required
⏭ Skipped | Deferred to later phase or replaced
Winner Values
Claude | Claude branch merged as-is
GPT | GPT branch merged as-is
Cherry-pick | Specific files/functions taken from each branch
Re-run | Both branches had critical failures; prompt re-run
N/A | Non-A/B prompt — no comparison needed
— | Not yet determined
Track Colors
A — Social App | Flutter social app completion
B — React Admin | React admin app (scaffold → parity)
C — Backend/Schema | Node.js API + PostgreSQL schema
D — LLM Pipeline | Moderation, analytics, event wrap reports
E — Jobs Board | Jobs marketplace + hire confirmation + ratings
A/B Test Protocol
A/B prompts | C0, A0, B0, C3, D0 (5 of 20 total)
Branch pattern | feature/{id}-{name}/{claude¦gpt}
Panel evaluators | Correctness · Security · Test Coverage · Patterns
Panel model | claude-opus-4-6 or gpt-5.4 (NOT the model being tested)
Merge rule | Winner squash-merged; loser branch archived
Calibration goal | Learn model strengths on IN codebase; commit to winner for rest of track
Key Files
docs/codex/README.md | Prompt template, A/B protocol, acceptance criteria guide
docs/codex/tracks.md | All 20 prompts, dependencies, status tracker
docs/codex/ADVERSARIAL_PANEL_TEMPLATE | Four role evaluator prompts (Correctness/Security/Tests/Patterns)
docs/codex/log/ | One completion log per executed prompt
docs/codex/reviews/ | One adversarial review doc per A/B prompt
docs/product/master_plan_v2.md | Architecture decisions — read before every prompt
CLAUDE.md | Full project reference — read before every prompt